Meeting Minutes – Hospital System ASB Cohort Meeting, 1000 on October 6th:

| Goal: | Plan: | Do: | Study: | Act: |
| --- | --- | --- | --- | --- |
| Reduce inappropriate prescribing of antibiotics for UTIs from 50% to < 30% | Education: Weekly pearls (Tuesdays) at Safety Huddle, ED Flash meetings Quiz to be performed at baseline & 2nd week of December Flyer to be hung in break rooms, depts for clinical staff UTI algorithm to be hung up near physician work areas, posted to Intranet Department champions to be selected for monthly staff educations in each department | Education: Yuan/Jessica/Amy to create a clinical pearls flyer 5-10 question quizzes to be sent out via Safety Huddle, Mary Baker, handed to department heads Ask Dr. Lynch to record a 5-minute PSA on ASB to share with physician staff to be posted to Intranet | Education: Yuan to research clinical pearls in partnership with Amy for flyer Follow up with reflex culture parameters (Lani/Jessica) | Education: 10/6: Emailed Natalia about Dr. Lynch video recording proposal 10/6: Jessica to set up a time with Lani in regards to gathering local data for ATH inappropriate prescribing baseline 10/6: Diane was emailed about urine reflex culture parameters 10/8: Submit ticket to IT requesting UTI Algorithm be posted to Intranet 10/15: Pearls flyer draft is due to ATH/ASH 10/15: Quizzes are sent out to Safety Huddle, hard copies given to departments 10/19: Begin sharing weekly clinical pearls based on flyers 10/22: Quizzes are emailed/handed back to Kimberly/Lani at ATH, Jessica/Yuan at ASH) 10/29: Prize is awarded via random drawing, department champions are picked and spoken to |
|  | Nudges: Develop a process when ordering UAs in Cerner Add a report-out phrase in C + S results for urine cultures Gather data on results (# of eRx for UTIs in ED, DOT of antibiotics?) | Nudges: Look around at what other Cerner Community Works Hospitals are doing, mimic their processes Jessica to speak to lab manager this month about adding report-out phrase | Nudges: Learn about how culture processes are done in the ED from a workflow perspective | Nudges: 10/6: Ask IT clinical staff to look in Cerner Community Works Forum regarding ASB UA processes By End of October: Jessica to learn how UA processes are done in ASH ED November Meeting: Discuss further the UA process nudge, models of how other hospitals are going about this |